## process steps
STEP |  | Station | supplies | minutes | time ending
Sat 1 | install sides in mold. check size of top and back to sides in mold, make reference marks on sides (which side down), trim length of sides, reinstall sides in mold (no glue) | 3 trim stations | 1/4 spacer to mark brace ends on drwg | 20 | 9:20
Sat 2 | Mark tops of neck and butt blocks to trim. For the long braces, mark drwg on workboard 1/4 inch in from sides. Remove sides and mark braces per marks on drwg. Trim braces and neck and butt blocks |  |  | 20 | 9:40
Sat 3 | Draw centerline on ugly side of soundboard and back. Use paper templates to mark brace locations on soundboard and back. |  |  | 15 | 9:55
Sat 4 | invert go-bar press to glue back and top braces simultaneously in go-bar press. Sand middle back brace to 5' radius and place 1/16 shim (5 business cards) under the center of the back. Note time and leave go-bars in place 1 hour |  | GBP, 12 long GBs, cauls, rim caul, cork, glue, straw | 30 | 10:25
Sat 5 | flatten neck and fretboard as required | flattening station | helpers can do this while students are gluing their braces | 20 | 10:45
Sat 6 | make drill guide block | drill press | transfer pins, 6mm brad point bit | 15 | 11:00
Sat 7 | add side marker dots to fretboard (for RH or LH player) |  | pin vise, 1/16 drill bit, superglue | 15 | 11:15
Sat 8 | chamfer fret slots |  | 3 corner file | 15 | 11:30
Sat 9 | sand fretboard |  | 220, 320, 400 grit | 15 | 11:45
Sat 10 | invert go-bar press and glue butt and neck blocks to sides in mold |  | glue, 2 clamps, waxed paper, straw | 15 | 12:00
Sat 11 | Dry fit and trim lining. Glue lining to sides using clothes pins. Note time and leave in place 1 hour |  | glue, 40 clothes pins w. rubber bands | 30 | 12:30
| LUNCH |  | lunch | 40 | 13:10
Sat 12 | straighten fret wire, cut frets to length |  | diagonal pliers, tapered block | 15 | 13:25
Sat 13 | invert sides in mold. Dry fit, trim, and glue other set of lining to the sides using clothes-pins. Note time and leave 1 hour |  | glue, 40 clothes pins and rubber bands | 30 | 13:55
Sat 14 | index fretboard to neck with 1/16 pins |  | drill, 1/16 bit, brass pins | 15 | 14:10
Sat 15 | install all frets | fret press |  | 45 | 14:55
Sat 16 | file fret ends flat and beveled |  | nipper, flat file, slotted file block | 15 | 15:10
Sat 17 | screw 4 blocks to workboard to restrain upper and lower bouts, flatten both gluing surfaces with 12" sanding disc, start with the side you glued first |  | 4 blocks and screws, sanding disc | 45 | 15:55
Sat 18 | remove one waist block from workboard, trim tabs from soundboard, fit soundboard to workboard holding in place with repositioned blocks and screws, reinstall waist block |  |  | 15 | 16:10
Sat 19 | with top, sides and back carefully aligned, glue top and back to sides simultaneously in go-bar press |  | GBP, 10 short (red) GBs, glue, rim caul | 40 | 16:50
Sat 20 | shorten brass pins as needed then glue fretboard to neck. |  | clamp (headstock to bench), 1/16 brass pins, big rubber band | 15 | 17:05
Sun 1 | Trim top and back with router | router table | Trim router on board with downcut spiral | 20 | 9:20
Sun 2 | touch up neck area of body with sandpaper |  |  | 10 | 9:30
Sun 3 | drill body with guide block |  | drill, 6mm brad point bit, large clamp to hole drill block in place | 20 | 9:50
Sun 4 | Fit neck to body (no glue) |  | file, sandpaper, straightedge | 30 | 10:20
Sun 5 | Sand body |  | 220, 320, PVC pipe sanding caul | 30 | 10:50
Sun 6 | neaten fret ends |  | 400 grit paper | 20 | 11:10
Sun 7 | trim and sand neck to match fretboard. sand neck w 120, 150, and 220 (finish) |  | file, sanding caul, 120, 150 & 220 grit | 30 | 11:40
Sun 8 | witness marker on frets, sand to flatten | flattening station | chisel point sharpie, 320 grit paper | 15 | 11:55
Sun 9 | glue neck to body, clamp fret board. Note time, leave 45 minutes |  | big rubber band, c-clamp w. caul | 60 | 12:55
Sun 10 | locate bridge w. template, drill index holes, mask around bridge, glue and clamp bridge |  | glue, neck/bridge template, 1/16 drill, round toothpicks, masking tape | 20 | 13:15
| LUNCH (LONG) |  | lunch | 90 | 14:45
Sun 11 | break off toothpicks, sand slot bottom |  | saddle slot sanding tool | 10 | 14:55
Sun 12 | crown frets |  | 400 grit paper | 15 | 15:10
Sun 13 | install tuners |  | 1/16 drill, #0 Phillips | 30 | 15:40
Sun 14 | install strings |  |  | 20 | 16:00
Sun 15 | simulate .020 at 1st fret, measure 12th fret action |  | capo, 2 business cards, action gage (helpers) | 15 | 16:15
Sun 16 | scribe saddle to desired height |  | calipers (helpers) | 10 | 16:25
Sun 17 | sand bottom of saddle and bottom of nut as required |  |  | 5 | 16:30
Sun 18 | glue nut to neck |  |  | 5 | 16:35
Sun 19 | fill defects with colored epoxy if required |  | JB Weld (wood), nitrile gloves | 10 | 16:45
Sun 20 | optional - apply shelac sealer |  |  | 10 | 16:55

## prep tasks
task group | task | description | where, when | who | cost estimate
drawings | copies | make 40 drawing copies |  | Al K | 20
| top braces | cut top brace locations in 10 copies |  | Al K | 0
| back braces | cut back brace locations in 10 copies |  | Al K | 0
| workboard | tape 20 copies to workboards |  | Carl L | 0
go-bar presses | plywood | obtain enough 3/4 plywood for 20 presses, cut plywood into 12x24 pieces, drill corner holes for legs, transport to St. M |  | Carl L | 180
| legs | obtain nice 2x4s for 80 legs, rip to 2x2, cut lengths to 23.5, drill shallow starter holes in ends, transport to St. M |  | Carl L | 50
| hardware | obtain 160 long construction screws, obtain 600 of 1-1/4 drywall screws |  | Carl L
| mold cauls | design and make wood mold cauls, 40 rectangular blocks and 40 rounded blocks |  | Carl L
| final assembly | assemble go-bar presses (legs, taped drwg, and mold cauls) |  | Carl L
| go-bars | determine number and lengths of go-bars required, cut poplar 3/4 x 5/32 poplar strips (or other tested material) |  | Al K
| rim cauls | make 20 rim cauls 1/8 inch thick |  | Al K
| cork | determine number of small cork pads, obtain and cut pieces |  | Al K
| 1/4 spacers | 20 little 1/4 spacer blocks to mark brace ends on drwg |  | Al K
| little blocks | provide 80 small blocks and screws to hold soundboard in place on workboard when gluing top and back to sides |  | Al K
lining clamps | clothes pins | obtain 40 clothes pins and rubber bands per station to clamp linings |  | Al K
bridge clamps | bridge clamps | Make 20 cam clamps |  | Carl/Bill
bridge location | bridge location | following Ian's design, make 4 templates to locate bridge relative to neck and nut |  | Al K
block clamps | block clamps | find 40 small clamps to clamp neck blocks and butt blocks, and some spring clamps
drill guides | prep drill guides | cut 20 blocks to be used as guides with 6mm transfer pins. |  | Norm
| drill the guides | setup and man the drill press to drill the guide block holes, 6mm brad point | at St. M, Saturday pm
bench hooks | bench hooks | round up 3 gent's saws, make 3 or more bench hooks to cut braces, sides, (and misc?), setup 3 stations | at St. M
fretting | tapered blocks | make 20 tapered blocks to aid cutting frets to length |  | Carl L
top & back trim | top & back trim setup | obtain trim router and piloted downcut spiral bit, mount router to a board |  | Al K
|  | setup trim station | at St. M
|  | man the station to trim tops and backs | at St. M, Saturday pm
extra tools | drills | round up some cordless drills and drill bits, return after workshop |  | Norm
| 6mm bits | obtain several 6mm brad point bits |  | Bill
| files | round up 9 flat single cut files, return after workshop |  | Al K
| file blocks | make 9 guide blocks each with 2 slots - 1 at 90 and 1 at 60 |  | Al K
| triangle files | find 5 t0 10 swiss pattern needle files (to ease fret slots)
| plastic hammers | find 2 or 3 plastic hammers to assist in fretting
| diagonal pliers | round up a few diagonal pliers for cutting frets |  | Norm
| pliers | round up a few pliers for misc use |  | Norm
| flush cut nippers | bring 2 good nippers |  | Al/ Carl
| 24 inch rulers | obtain a few straight edges, manage their return |  | Norm
| #2 phillips | round up several #2 phillips screwdrivers, or long drivers for drills |  | Norm
| glue brushes | obtain at least 20 glue brushes |  | Al K
| glue bottles | obtain 20 small squeeze bottles for glue |  | Al K | 17
supplies | sandpaper | bring 20 quarter sheets each of 220, 320, 400 |  | Al K
| round sanding cauls | provide 20 pcs of 3/4 PVC 4.5" long |  | Al K
| sanding discs | make 20 of 12" diam sanding blocks to flatten gluing surface for front & back |  | Al K | 0
| sanding station | setup a flat surface sanding station for necks/fretboards |  | Carl L
| brass rod | provide 40 small pcs of 1/16 brass rod |  | Al K
| filler | bring JB Weld wood filler |  | Al K
| superglue | buy small containers of thin super glue |  | Bill
| blue tape | obtain a few rolls |  | Al K
| waxed paper | obtain one roll |  | Al K
| paper bowls | obtain disposable water bowls for each workstation, obtain an empty gallon jug to distribute water |  | Al K
| Name tags | bring 50 peel & stick name tags |  | Bill
video screens | video screens | determine if using video cameras and screens will help, coordinate using them with FLWT, setup and operate at workshop |  | Al K
manage layout | manage layout | plan and direct volunteers to re-arrange worktables at St. M | at St. M
tool-kits | tool kits | manage the collection, distribution, and return of all tools and supplies at the workshop | at St. M
release forms | release forms | collect all release forms as participants arrive | at St. M
follow-up list | follow-up list | document and schedule follow-up actions that come up during the workshop | at St. M